## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
Coding Phase complete. Testing Phase underway. Dates Adjusted to match meetings. | 
Status as of | 08-April-20
Business Lead | Jim Worth
Project Manager | Daniel Marzari
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/22 | 
Design |  | 100% | 2/29 | 
Coding |  | 100% | 3/28 | 4/4
SIT - System Test |  | 75% | 4/4 | 4/15
UAT User Acceptance Test |  | 0% | 4/11 | 4/15
Training and Doc |  | 30% | 5/2 | 
Deployment |  | 0% | 4/18 | 
Go Live |  | 0% | 5/9 | 
Hyper Care |  | 0% | 4/25 | 
# | Key Accomplishments (Current Period)
1 | All pages complete and connected
2 | Alumni authentication complete
3 | Alumni Security complete
# | Upcoming Activities (Next Period through (03/25/2019)
1 | Admin Security
2 | Additional Systems Testing (local)
3 | Plan Deployment
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | None | Low | Low | None | Daniel Marzari | Low | --/--
AlumniConnect
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | None | Low | Low | None | Daniel Marzari | Low | --/--